**Joint Accessibility Advisory Committee**

**Work Plan for 2022**

Updated: August 13, 2021

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Deliverable / Project | Description | Frequency | Scheduled Date | Location | Lead | Status | Deadline | Budget/Comments |
| 1. | Ramp Program | To continue review of current ramp program with a view to implementing a more user-friendly program. | Monthly review of applications if any received.  |  |  |  | On-going review of best possible solutions for a ramp program  |  | $10,000 budget carryover from 2020 request to Council |
| 2. | Abilities Fair | Once Public Health Guidelines Permit. | Annual |  |  |  | Originally planned for Spring 2020. Due to COVID-19 event was cancelled. If public heath guidelines permit an Abilities Fair could be planned for Fall of 2022  |  | $10,000 from 2021 budget special projects |
| 3. | Tip of the Month | To provide an accessibility tip on a monthly basis for the Town page in newspaper and on the accessibility page of the Town’s website.  | monthly |  |  |  |  | Due at each monthly meeting | Provided monthly by Committee member. Committee votes on tip each month for selection.  |
| 4. | Town of Orangeville Accessibility Plan | To update Town accessibility plan. | Annual review |  |  |  |  |  | To be completed in-house. If consulting services required $5,000 from 2020 special projects budget.  |
| 5. | Rack cards/post cards | Marketing and promotion of the committee to the public | Annually |  |  |  | As public health guidelines permit and the committee is able to be more active in the community this initiative may be completed |  | $2,000 printing cost |
| 6. | Education for Audio Pedestrian Signals | A program or instruction guide to facilitate the use of the audio pedestrian signals at Town crosswalks | One time event |  |  |  | As public health guidelines permit the committee will determine a timeline for this initiative |  |  |
| 7. | Communication Boards | An installation used at community parks to increase accessibility |  |  |  |  | The committee is still in the investigative stages of this initiative but may wish for fall 2022 implementation. |  |  |
| 8. | Accessibility Awards | Awards for businesses and service groups within the County of Dufferin  | Annual event | Accessibility Month, 2022 |  |  | Committee to determine criteria for award |  |  |